## Checkpoints
Checkpoint 1 (Week 5) Inception and Setup 2.5 / 60 | Deliverables | Complete?
| Team Formation | Y | https://canvas.qut.edu.au/courses/23242/pages/assessment-1-description-project-progress-and-performance-checkpoints
| Project Requirements | Y
| Project Repository | Y
| ALL Java Readiness Quizzes | Y
Checkpoint 2 (08.04.2026) Planning and Design 2.5 / 60 | Deliverables | Complete?
| User stories | Y
| Project Management Tool | Y
| Release Plan and First Sprint Plan | Y
| UI Design (Low/Medium Fidelity) | Y
| Evidence of Iteration | Y
Checkpoint 3 (Week 9) Implementation and Quality Assurance 2.5 / 60 | Deliverables | Complete?
| Functional Prototype | Y
| Test Driven Development | Y
| Version Control Workflow | Y
| Demo progress to Tutor | Y
Checkpoint 4 (Week 9 EOW) Preliminary Project Submission 20 / 60 | Deliverables | Complete?
| Preliminary Prototype | Y
Checkpoint 5 (Week 12 Continuous Integration 2.5 / 60 | Deliverables | Complete?
| Enhanced Prototype | N
| Build Script | N
| Automated Build Server | N
| Evidence of refactoring and OO design patterns | Y
Checkpoint 6 (Week 13 Friday End of Day) Finalised Project Submission 30 / 60 | Deliverables | Complete?
| Final Prototype, Demo | N

## 13.05.2026
Daniel | "an authentication system to sign-up/sign-in (GUI and models)" + User Database | a persistency system to store/retrieve/update user data (GUI and models) | Username Foreign Key, Overarching Database | Hash the strings | Test suite authentication
Ethan | Test suite automation | Server build
Jacob | Reminders
Nate | Refactoring
Nick | AI Integration

## FLAP
Future considerations | Lessons learned | Achievements | Problems
Communication | Clearer delegation of roles, whose domain belongs to who | Delivered functional prototye despite setbacks | Miscommunication and lack of mission clarity
Clearer goals and expectations | A better vision of what the final product look like | Goals completed on time | Still needs AI integration
Availiability | More consistent use of Agile principes throughout | Utilised feedback regarding Project Management tool well
Better undersanding of own limits and what is sustainable | Consistent communication = Better results | Tecnical skills developed. Coded Pomodoro / Trivia / Database from scratch
| Use of SOLID principles allowed for efficient merging | Everyone developed a more well rounded IT skillset e.g. Git merging, Agile
Play to your strengths, each member had a specialised doman
It's okay to ask for help

## User Testing
Purpose: | Find out the usability of the application, as well as usefulness |  | Feedback
Change Start Pause button Colours
What are we seeking to improve? | Usability, UI |  | Change "Rest" to "Break"
Trivia questions in a speech bubble
Research question : | How frequently would you use this application in daily life? |  | Knowing what to do on Sessions TableView. Hierarchy and embolden Text. Navigation buttons on the Top. More sign posting. Clearer navigation.
Change "Sessions" to "Sessions View" or "Sessions Data"
Change "Pomodoro" to "Timer"
Task Scenarios |  |  | Pet needs to be talking with speech bubbles every so often
1 | Move the pet to middle of screen |  | Return to Work / Rest - Change to an Arrow Shape button????
2 | Wait for the pet to move
3 | Click the pet so it jumps
4
| Excel Sheets United - User Testing – Fill out form | Excel Sheets United - User Testing – Results

## Availiabilities
Contact |  |  | Availiabilities | [7 empty] | Role(s)
Name | GitHub | Email | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Name | Product Owner | Developer | Scrum Master
Daniel | Cybrarian | n10245871@qut.edu.au | unavailable | 10am-10pm | 5pm-10pm | unavailable | 10am-10pm | 10am-10pm | 10am-10pm | Daniel |  |  | X
Ethan | Etherium64 | n10809155@qut.edu.au | 8am-3pm | 10am-3pm | 12pm-3pm, 5pm-7pm | N/A | 1pm-6pm | 10am-2pm | N/A | Ethan |  |  | X
Jacob | jakefarrell57 | n10145419@qut.edu.au | 10am-10pm | 12pm-5pm | 12pm-5pm,5pm-7pm | 10am-10pm | 10am-10pm | ~10am-10pm | ~10am-10pm | Jacob |  |  | X
Mak | MakovinTep | n10106774@qut.edu.au |  |  | 5pm-7pm |  |  |  |  | Mak
Nate | natw5004 | n12498700@qut.edu.au | any time | unavailable | any time | unavailable | 3pm onwards | any time | unavailable | Nate | x |  | X
Nick | nickkin4 |  |  |  | 5pm-7pm |  |  |  |  | Nick
|  | Date | Time | Daniel | Ethan | Jacob | Mak | Nate | Nick | https://github.com/Etherium64/ExcelSheetsUnitedProject.git
|  | Wednesday, 18 March 2026 | 5pm-7pm | Y | Y | Y | Y | Y | Y
|  | 2026-03-25 | 340pm-7pm | Y | Y | Y | Y | Y | Y
Y
Note on M2: Author: Product backlog, Represents Customers and Stakeholders
Note on N2: Author: Programming, Testing, UX Design, Writing Documentation
Note on O2: Author: Facilitates Team Meetings and Overall Collaboration

## Sprint and Release Plan
Agile Sprint & Release Plan
Project Name |  | Desktop Pet |  |  |  | Start Date | End Date
Project Manager |  | Shared Responsiblity |  |  |  | 2026-03-11 | 2026-06-07
Project Deliverable |  | A basic companion application.
Scope Statement |  | The companion will perform basic animations on screen and provide trivia questions and a timer for users.
AT RISK | TASK NAME | RESPONSIBLE | STORY No. | START | FINISH | STATUS | COMMENTS
| SPRINT 1 | Daniel |  | 2026-03-25 | 2026-04-15
No | Pomodoro Research and Base Code | Daniel | 4, 5 | 25/03 | 15/04 | Complete
No | Paper Prototype and State Change Research | Jacob | 1 | 25/03 | 15/04 | Complete
No | Animation Reasearch and Basic Sprite Creation | Nate | 1 | 25/03 | 15/04 | Complete
No | Trivia Research and Basic Implementation | Ethan | 2 | 25/03 | 15/04 | Complete
No | Basic Framework for Application. | Nick | NA | 25/03 | 15/04 | Complete
| SPRINT 2 | Jacob |  | 2026-04-15 | 2026-04-29
No | Construct Pomodoro Timer with Database to Store History | Daniel | 6 | 16/04 | 29/04 | Complete
No | Create Trivia Module with Database for Questions and Answers | Ethan | 3 | 16/04 | 29/04 | Complete
No | Construct State Machine for Animated Sprite | Jacob | 7, 8, 9 | 16/04 | 29/04 | Complete
No | Create Animations for State Machine | Nate | 7, 8, 9 | 16/04 | 29/04 | Complete
No | Merging current work and branches and preliminary work on advanced UI. | Nick | NA | 16/04 | 29/04 | Complete
| SPRINT 3 | Jacob |  | 2026-04-29 | 2026-05-20
No | Refining pomodoro timer and implementing a test suite. | Daniel | 4, 5, 6 | 30/04 | 20/05 | Complete
No | Refining state change machine and refactoring. Implementing JavaDoc comments. | Jacob | NA | 30/04 | 20/05 | Complete
No | JavaDoc automation with build server and scripts. | Ethan | NA | 30/04 | 20/05 | Complete
No | Refacoring animation feature and updating sequences. | Nate | 1, 7, 8, 9 | 30/04 | 20/05 | Complete
No | Tranparent feature implemenation and refactoring. | Nick | NA | 30/04 | 20/05 | Complete
| SPRINT 4 | Jacob |  | 2026-05-21 | 2026-05-27
No | AI trivia implementation and refactoring. | Nick | 2 | 21/05 |  | Complete
No | Test suite for pet class and organising presentation. | Jacob | NA | 21/05 |  | Complete
No | Authentification feature, unifying databases and refactoring. | Daniel | 2, 6 | 21/05 |  | Complete
No | Presentation preparation and organising submission. | Ethan | NA | 21/05 |  | Complete
No | Presentation preparation and organising submission. | Nate | NA | 21/05 |  | Complete

## 18.03.2026
Date | Wednesday, 18 March 2026
Start Time | 17:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick, Makovin
Apologies | N/A
Item | Summary | From
Project Idea | Anti AI position (?) deliberate Satire
| Desktop Pet / Study Buddy / Shimeji | Jacob/
| https://kilkakon.com/shimeji/ | Daniel
UX Design | Rat (Daniel's Dog) | Jacob
Clippy (Satire)
Creative commons images
https://search.creativecommons.org/
| Unity assets | Daniel
https://assetstore.unity.com/top-assets/top-free
| 2D (Much easier, preferred) vs 3D (More dynamic, 'alive') Animation | Nick, Jacob, Ethan
| Comissioning artists. Tutor says this is OK as Agile and Java Development is being graded only, but MUST credit. | Nick(?)
Programming | What is the Desktop Pet's functionality?
| Reminds students to take a break, drink water | Ethan
| Pomodoro Timer | Daniel
Can drag pet around the Desktop w/ Cursor
Open-source AI for Q&A querying function. Ask questiones and Pet outputs answer.
API connect to a Pre-built Java code base
| Sycophantic dialogue, AI Hallucination (Satire) | Jacob/
Scrum | Create ESU Discord w/ #general, #git-names, #git-repository, #record-keeping, #trouble-shooting threads | Ethan
| Set up GitHub repositry and invited members | Ethan
| https://github.com/Etherium64/ExcelSheetsUnitedProject.git | Ethan
| Team Formation. Nate brings friend Mak for full team of Six. Welcome to Excel Sheets United! | Daniel, Nate
| Excel workbook to manage information for Availiabilities, Check Points, Meeting Minutes, | Daniel
| Apply for assignment extesion if required | Daniel
Troubleshooting | "Cannot resolve Symbol" error | Daniel, Nate
File > Invalidate Caches File > Project Structure. Ensure correct directory pathway Uninstall and reinstall Amazon Coretto. Ensure v21
To Do Before Checkpoint | Arrange another meeting
| Complete Java Readiness Modules | All
| Project Brief | Jacob
Research for Programming
Research for UX design
| Create Excel workbooks and upload to GitHub | Daniel

## 25.03.2026
Date | Wednesday, 25 March 2026
Start Time | 15:40
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick, Makovin
Apologies | N/A
Item | Summary | From
Programming / Testing | Set up the concept framework in repository | Ethan
| Attempt github pull, Git pull origin framework | Nate
Troubleshooting | Nate's Java IDLE not working, cannot create a new JavaFX Project
| Uninstall and reinstall JetBrains | Daniel, Ethan, Nate
https://canvas.qut.edu.au/courses/23242/pages/integrated-development-environment-setup-5?module_item_id=2192493
| How to co-ordinate GitHub pulls, branches, commits across team | Ethan, Nate
| Write documentation for GitHub and set up a branch plan | Ethan, Nate
Project set up / Research | Project set up - What type of AI-based Desktop Pets? | Nate
| State Machine implementation | Nate
| Happy sad angry emotion functionality | Ethan
| Open source codebase and Rest API | Nate
| What is the functionality? Start simple and with user stories | Ethan
| Monitoring study companion - hey have you had water? You've been staring at screen 1 hour? Don't neglect your health | Ethan
| Anti vs Pro AI position? How does the project relate to the AI idea | Daniel
| A general commentary on AI and human interactions, start simple and avoid the satire idea for now | Ethan
| Output Trivias responses, customise Trivia subject matter | Ethan, Jacob
| Secret hidden game code - AI realises its alive!!!!! Advanced feature, Konami Code | Daniel, Ethan, Jacob
| Pomodoro Timer- easy to implement, basic functionality | Daniel
Scrum | How to organise your individual worklog - the workflow | Daniel, Ethan, Jacob
| Catching everyone up with Troubleshooting session and Branch plan | Ethan
Research | JavaSwing into JavaFX, research into JavaSwing may be easier only 120 lines of code | Nick
| Hijack Rest API Vtube studio, open-source Electron desktop pets, Javascript Open Source Mascot Assets Line | Nate
| Desktop functionality ideas: dialogue system, physics, rewards afferction system. Probably don't use multiple characters, just one characters. | Nate
Activity 1 Scrum Meetings | Daniel Scrum Master | Daniel
| 1) Excel sheets 2) Researching Shimeji + Pomodoro functionality + More Excel sheets) Still learning JavaScript | Daniel
1) Done last week | 1) Project Brief 2) User Stories + Low fidelity prototype 3) Still learning JavaScript | Jacob
2) To do this week | 1) Set up Github repositry + Discord server + Java HTML application menus 2) GitHub navigation document 3) IntelliJ IDLE issues | Ethan
3) Road blocks | 1) Java Readiness + Research existing Companions apps + Troubleshooting IDLE 2) Further research Companion apps + animation state machines in Java e.g. Reaction system that selects actions that you can interrupt 3) Intellji IDLE issues | Nate
| 1) Went through Assignbment briefing and made a low fidelity demo for Desktop pet 2) Continue improving demo, implementing animation, AI 3) Debugging | Nick
| 1) Java Readiness (Late addition to the group Sixth member) 2) Catching up on Content and Java knowledge + Nate's research assistant 3) Being a late addition Sixth group member | Mak
Project set up | Are we allowed to use JavaSwing??? | Nate
| JavaFx can't do window click through | Nate
| Do we want it to go anywhere on the screen or a select field | Ethan
| Scale the transparent window | Nate
| Split Desktop pet functionality into must haves vs nice to haves -> User StoriesTab | Ethan
Pre-existing Codebases allowed
Nick ask about JavaSwing Gui. Email pending for Unit Coordinator. JavaSwing has functionality where you can click windows and it won't break
Each member responsible for Branch. Keep pushing to main to make sure code is Compatabile.
Start with a seed, Basic JavaFX project
GitHub documentation | Create new project > Java FX, Maven, name it Nothing needs to be ticked Terminal > git remote add origin [link] (github take https) > Hit Enter Git add . git commit - m "text" git pull Now you have the remote branches Click "Framework" and check the branches Check project folders Main>Java>project.esu>Launcher>Play button Ensure Computer has the external libraries for Java FX | Ethan
Troubleshooting | Git being Git. Defer | Ethan
| Pomodoro + add a database (this many hours of work) --> stretch goal Virtual currency. Build in tools that assist uses by suggesting work break, drink water and eat | Daniel
Core Functionality MUST HAVES | Getting it on the screen Base programming. Windows. JavaFX only, can't use JavaSwing unfortunately. | Nick
| How to Github step by step documentation | Ethan
| Ask Trivia questions (can simulate AI doesn't have to integrate AI. Ai integration can be a stretch goal. Implement AI first before we decide what its supposed to comment about AI). State machine | Ethan
| Animation Design - Nate's discretion. Rigging? Free assets can use see above meeting minutes points | Nate
| Programming for the Animation. Interact with pet by clicking. State machine. Built in tools | Jacob
| Boot up apps + One time menu screen + Catch up with Content | Mak

## 01.04.2026
Date | Wednesday, 1 April 2026
Start Time | 15:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate
Apologies | Nick, Makovin
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master Daniel | Daniel
| 1) Researched Pomodoro 2) User Stories + Implement basic Pomodoro functionality + Release Plan 3) Still learning Javascript | Daniel
1) Done last week | 1) Research design and rig-testing models 2) Implement the animation model (PNG method?) 3) No roadblocks currently | Nate
2) To do this week | 1) GitHub documentation and Mock Trivia branch code 2) SQL Storage for Trivia 3) Working Github [solved] | Ethan
3) Road blocks | 1) User stories 2) Research state changes for animation 3) Working Github [solved] | Jacob
| 1) Currently sick. Working on App Baseline Fucntionality. 2) Finish prototype Baseline Functionality and commit to Git. 3) Getting better :) | Nick

## 15.04.2026
Date | Wednesday, 15 April 2026
Start Time | 14:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Week 5-7 Retrospective
| User Stories + Implement basic Pomodoro functionality + Release Plan | Daniel
| Implement the animation model (PNG method?) | Nate
Review Project Tasks | SQL Storage for Trivia | Ethan
| Research state changes for animation and prototype | Jacob
| Finish prototype Baseline Functionality and commit to Git. | Nick
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Nate
| 1) research into timers, difficulted with fxml, user stories 2 ) get it working, start score system with a DB 3) struggles with figuring out java and fxml, merging issiues | Daniel
1) Done last week | 1) animating the character, creating sprite sheets, made basic style sheet. 2) help merging of branches, help with state machines.set up Trello 3) waiting on mass merg of classes before adding to the fire | Nate
2) To do this week | 1) made the trivia module and store data into a DB, ensureed it was ra, set up a test suit,2) merge to master branch 3) database issues but they are mainly fixed, git merges | Ethan
3) Road blocks | 1) mainly focused on the paper prototying, research into statemachains. 2) start working on the statemachine, 3) making it past the staticness of fxml | Jacob
| 1) finished the skeleton code for pulling up images, figuring out the logic 2) merg app, restructering to fit the rest of the program 3) waiting merger and debugging | Nick

## 22.04.2026
Date | Wednesday, 22 April 2026
Start Time | 14:30
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Daniel
| 1) Functional timer implementation timer + database research 2) Fixing buttons Timer + Database Pomodoro integration with Score 3) Needs further testing | Daniel
1) Done last week | 1) State changes code based off Nick's branch code and separating into code files 2) Combining state-machine with animation 3) None so far | Jacob
2) To do this week | 1) Merging all coding branches and debugging gitHub 2) Set up test suites for the others and implement Java documentation 3) Renamed SDK files | Ethan
3) Road blocks | 1) Set up Trello sprint plan for others to contribute , Finalising animation 2) Integrating the animation with the state machine code, setting up Animation Classes to get 3) Unsure if will work with current State Machine | Nate
| 1) Finished coding Skeleton code Double checked Pomodoro, Trivia and other code to see how they merge. 2) Start on merging everything with Skeleton code. 3) Understanding other team mates code. | Nick

## 29.04.2026
Date | Wednesday, 22 April 2026
Start Time | 14:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Jacob
| 1) Refining pomodoro timer, making sure the timer doesnt duplicate, sophisticating the database 2) adding documentation and proper testing 3) test suite | Daniel
1) Done last week | 1) Refining the state change machine, implementing UI and animations 2) Ironing out bugs, polishing the UI, Javadoc comments 3) javadocs comments | Jacob
2) To do this week | 1) Set up javadoc automation, a lot of merging of branches (A LOT), javadocs commenting for trivia section, overlay for trivia with desktop pet 2) polishing UI for the trivia when called, helping merge and everything stable 3) INTELLIJ SUCKS | Ethan
3) Road blocks | 1) Worked on setting up on image sequences, and made it customisable and simpler to call 2) Adding in Javadocs comments and fixing up animations and colour variants 3) No roadblocks thanks Ethan | Nate
| 1) Merging branches together to get it working together for transparent prototype, adding features (timer, pomodoro) 2) UI and feature box 3) debugging | Nick

## 06.05.2026
Date | Friday, June 5, 2026
Start Time | 17:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Daniel
| 1) Assisted with transparent overlay of TableView FXML and troubleshooting 2) Polishing the overall App , User Testing 3) Time | Ethan
1) Done last week | 1) Video editing for Assignment 2 and fixed Drag error 2) Refactoring and applying Encapsulation OOP principles, JavaDoc, bounds for Pet, User Testing 3) Time | Jacob
2) To do this week | 1) Fixed up Animation code and State Change code, Java Documentation 2) Update animations specifically renders so that there is less dead space and smoothing out, Refactoring Code, User Testing 3) Recovery and time | Nate
3) Road blocks | 1) Recorded video part, Refactoring the Skeleton code, 2) Start compiling everything into Transparent version. Refactoring. Implement AI into Ethan's Trivia module, User Testing 3) Time and debugging | Nick
| 1) TableView, CRUD operations, Integrate Pomodoro into SCA, User Testing and Documentation 2) Refactoring, User Testing, Refine Pomodoro overlay especially on TableView 3) Debugging issues | Daniel

## 20.05.2026
Date | Friday, June 5, 2026
Start Time | 17:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Ethan
| 1) fixed trivia layout, implemented the automation for test suite. 2) record video for final submission video. 3) time | Ethan
1) Done last week | 1) refectored code and added pet object class, added java do comments and worked on presentation outline. 2) refine presentation, get feedback, create test suite for desktop pet module. 3) communication about final refactoring with desktop pet module. | Jacob
2) To do this week | 1) fixing aspect ratio, added shock emote to replace jump, refactored code to strengthen oo priciples, got user testing feedback. 2) work on presentation and video for final submission. 3) not much. | Nate
3) Road blocks | 1) set up authentication gui, setup unified database, refeactored database and other code. 2) implement user feedback. 3) time. | Daniel
| not present | Nick

## User stories
Functionality Ideas |  | Must Haves | Should have | could have | Won't have
Idle actions
Interact with pet by clicking |  | Y
locked at bottom 1/4 of screen
asks random trivia questions (simulating AI) |  | y
Pomodoro Timer, Logging successful sessions on database |  | Y
shake the pet it gets mad
click pet it gets happy
ignore/neglect pet it gets sad
Konami Code
Sound effects
Virtual currency for successful Pomodoro sessions
Build in tools that assist uses by suggesting work break, drink water and eat |  | Y
required animations | idle | BLOCKED
| walking (types?) | BLOCKED LEFT AND RIGHT
interaction
reacting
sleeping
state transition
timed events
random events
talking
| jumping | BLOCKED
yawning
| blinking | IN THE IDLE
sneezing
head tilt
hanging while picket up
| crying | TOO MUCH WORK
| interact with props | no props added /made
wave
speaking
| give coin to user | very much a stretch goal
wide eye stare into camera
required expressions | happy | done
| sad | done
bored
confused

## Sprint Plan OLD
| User Stories Summary | Week 5 | Week 6 | Week 7
Daniel | Pomodoro | Researching functionality | Implemented basic functionality | Uploaded Pomodoro GUI
Ethan | Trivia | Mock Trivia branch code | SQL Storage for Trivia | Set up the TriviaModule test suit
Jacob | State Machine | Low fidelity paper prototype | Research state changes | Implementing state change machine
Nate | pet creation/ finding | animations | creating sprite sheets | sql database to store anims
Nick | Skeleton | Low fidelity pet demo | Baseline functionality | Merging together