## Checkpoints
Checkpoint 1 (Week 5) Inception and Setup 2.5 / 60 | Deliverables | Complete?
| Team Formation | Y | https://canvas.qut.edu.au/courses/23242/pages/assessment-1-description-project-progress-and-performance-checkpoints
| Project Requirements | Y
| Project Repository | Y
| ALL Java Readiness Quizzes | Y
Checkpoint 2 (08.04.2026) Planning and Design 2.5 / 60 | Deliverables | Complete?
| User stories | Y
| Project Management Tool | Y
| Release Plan and First Sprint Plan | Y
| UI Design (Low/Medium Fidelity) | Y
| Evidence of Iteration | Y
Checkpoint 3 (Week 9) Implementation and Quality Assurance 2.5 / 60 | Deliverables | Complete?
| Functional Prototype | Y
| Test Driven Development | Y
| Version Control Workflow | Y
| Demo progress to Tutor | Y
Checkpoint 4 (Week 9 End of Day) Preliminary Project Submission 20 / 60 | Deliverables | Complete?
| Preliminary Prototype | N
Checkpoint 5 (Week 11) Continuous Integration 2.5 / 60 | Deliverables | Complete?
| Enhanced Prototype | N
| Build Script | N
| Automated Build Server | N
| Evidence of refactoring and OO design patterns | N
Checkpoint 6 (Week 13 Friday End of Day) Finalised Project Submission 30 / 60 | Deliverables | Complete?
| Final Prototype, Demo | N

## Availiabilities
Contact |  |  | Availiabilities | [7 empty] | Role(s)
Name | GitHub | Email | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Name | Product Owner | Developer | Scrum Master
Daniel | Cybrarian | n10245871@qut.edu.au | unavailable | 10am-10pm | 5pm-10pm | unavailable | 10am-10pm | 10am-10pm | 10am-10pm | Daniel |  |  | X
Ethan | Etherium64 | n10809155@qut.edu.au | 8am-3pm | 10am-3pm | 12pm-3pm, 5pm-7pm | N/A | 1pm-6pm | 10am-2pm | N/A | Ethan |  |  | X
Jacob | jakefarrell57 | n10145419@qut.edu.au | 10am-10pm | 12pm-5pm | 12pm-5pm,5pm-7pm | 10am-10pm | 10am-10pm | ~10am-10pm | ~10am-10pm | Jacob |  |  | X
Mak | MakovinTep | n10106774@qut.edu.au |  |  | 5pm-7pm |  |  |  |  | Mak
Nate | natw5004 | n12498700@qut.edu.au | any time | unavailable | any time | unavailable | 3pm onwards | any time | unavailable | Nate | x |  | X
Nick | nickkin4 |  |  |  | 5pm-7pm |  |  |  |  | Nick
|  | Date | Time | Daniel | Ethan | Jacob | Mak | Nate | Nick | https://github.com/Etherium64/ExcelSheetsUnitedProject.git
|  | Wednesday, 18 March 2026 | 5pm-7pm | Y | Y | Y | Y | Y | Y
|  | 2026-03-25 | 340pm-7pm | Y | Y | Y | Y | Y | Y
Y
Note on M2: Author: Product backlog, Represents Customers and Stakeholders
Note on N2: Author: Programming, Testing, UX Design, Writing Documentation
Note on O2: Author: Facilitates Team Meetings and Overall Collaboration

## Sprint and Release Plan
Agile Release Plan Template
Project Name |  | Desktop Pet |  |  |  | Start Date | End Date | Overall Progress
Project Manager |  | Shared Responsiblity |  |  |  | 2026-03-11 |  | 0%
Project Deliverable |  | A basic companion application.
Scope Statement |  | The companion will perform basic animations on screen and provide trivia questions and a timer for users.
AT RISK | TASK NAME | RESPONSIBLE | STORY No. | START | FINISH | STATUS | COMMENTS
| SPRINT 1 | Daniel |  | 2026-03-25 | 2026-04-15
No | Pomodoro Research and Base Code | Daniel | 4, 5 | 25/03 | 15/04 | Complete
No | Paper Prototype and State Change Research | Jacob | 1 | 25/03 | 15/04 | Complete
No | Animation Reasearch and Basic Sprite Creation | Nate | 1 | 25/03 | 15/04 | Complete
No | Trivia Research and Basic Implementation | Ethan | 2 | 25/03 | 15/04 | Complete
No | Basic Framework for Application. | Nick | NA | 25/03 | 15/04 | Complete
| SPRINT 2 | Jacob |  | 2026-04-15 | 2026-04-29
No | Construct Pomodoro Timer with Database to Store History | Daniel | 6 | 16/04 | 29/04 | Complete
No | Create Trivia Module with Database for Questions and Answers | Ethan | 3 | 16/04 | 29/04 | Complete
No | Construct State Machine for Animated Sprite | Jacob | 7, 8 | 16/04 | 29/04 | Complete
No | Create Animations for State Machine | Nate | 7, 8 | 16/04 | 29/04 | Complete
No | Merging current work and branches and preliminary work on advanced UI. | Nick | NA | 16/04 | 29/04 | Complete
| SPRINT 3 | Jacob |  | 2026-04-29 | 2000-01-01
30/04
30/04
30/04
30/04
30/04

## 18.03.2026
Date | Wednesday, 18 March 2026
Start Time | 17:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick, Makovin
Apologies | N/A
Item | Summary | From
Project Idea | Anti AI position (?) deliberate Satire
| Desktop Pet / Study Buddy / Shimeji | Jacob/
| https://kilkakon.com/shimeji/ | Daniel
UX Design | Rat (Daniel's Dog) | Jacob
Clippy (Satire)
Creative commons images
https://search.creativecommons.org/
| Unity assets | Daniel
https://assetstore.unity.com/top-assets/top-free
| 2D (Much easier, preferred) vs 3D (More dynamic, 'alive') Animation | Nick, Jacob, Ethan
| Comissioning artists. Tutor says this is OK as Agile and Java Development is being graded only, but MUST credit. | Nick(?)
Programming | What is the Desktop Pet's functionality?
| Reminds students to take a break, drink water | Ethan
| Pomodoro Timer | Daniel
Can drag pet around the Desktop w/ Cursor
Open-source AI for Q&A querying function. Ask questiones and Pet outputs answer.
API connect to a Pre-built Java code base
| Sycophantic dialogue, AI Hallucination (Satire) | Jacob/
Scrum | Create ESU Discord w/ #general, #git-names, #git-repository, #record-keeping, #trouble-shooting threads | Ethan
| Set up GitHub repositry and invited members | Ethan
| https://github.com/Etherium64/ExcelSheetsUnitedProject.git | Ethan
| Team Formation. Nate brings friend Mak for full team of Six. Welcome to Excel Sheets United! | Daniel, Nate
| Excel workbook to manage information for Availiabilities, Check Points, Meeting Minutes, | Daniel
| Apply for assignment extesion if required | Daniel
Troubleshooting | "Cannot resolve Symbol" error | Daniel, Nate
File > Invalidate Caches File > Project Structure. Ensure correct directory pathway Uninstall and reinstall Amazon Coretto. Ensure v21
To Do Before Checkpoint | Arrange another meeting
| Complete Java Readiness Modules | All
| Project Brief | Jacob
Research for Programming
Research for UX design
| Create Excel workbooks and upload to GitHub | Daniel

## 25.03.2026
Date | Wednesday, 25 March 2026
Start Time | 15:40
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick, Makovin
Apologies | N/A
Item | Summary | From
Programming / Testing | Set up the concept framework in repository | Ethan
| Attempt github pull, Git pull origin framework | Nate
Troubleshooting | Nate's Java IDLE not working, cannot create a new JavaFX Project
| Uninstall and reinstall JetBrains | Daniel, Ethan, Nate
https://canvas.qut.edu.au/courses/23242/pages/integrated-development-environment-setup-5?module_item_id=2192493
| How to co-ordinate GitHub pulls, branches, commits across team | Ethan, Nate
| Write documentation for GitHub and set up a branch plan | Ethan, Nate
Project set up / Research | Project set up - What type of AI-based Desktop Pets? | Nate
| State Machine implementation | Nate
| Happy sad angry emotion functionality | Ethan
| Open source codebase and Rest API | Nate
| What is the functionality? Start simple and with user stories | Ethan
| Monitoring study companion - hey have you had water? You've been staring at screen 1 hour? Don't neglect your health | Ethan
| Anti vs Pro AI position? How does the project relate to the AI idea | Daniel
| A general commentary on AI and human interactions, start simple and avoid the satire idea for now | Ethan
| Output Trivias responses, customise Trivia subject matter | Ethan, Jacob
| Secret hidden game code - AI realises its alive!!!!! Advanced feature, Konami Code | Daniel, Ethan, Jacob
| Pomodoro Timer- easy to implement, basic functionality | Daniel
Scrum | How to organise your individual worklog - the workflow | Daniel, Ethan, Jacob
| Catching everyone up with Troubleshooting session and Branch plan | Ethan
Research | JavaSwing into JavaFX, research into JavaSwing may be easier only 120 lines of code | Nick
| Hijack Rest API Vtube studio, open-source Electron desktop pets, Javascript Open Source Mascot Assets Line | Nate
| Desktop functionality ideas: dialogue system, physics, rewards afferction system. Probably don't use multiple characters, just one characters. | Nate
Activity 1 Scrum Meetings | Daniel Scrum Master | Daniel
| 1) Excel sheets 2) Researching Shimeji + Pomodoro functionality + More Excel sheets) Still learning JavaScript | Daniel
1) Done last week | 1) Project Brief 2) User Stories + Low fidelity prototype 3) Still learning JavaScript | Jacob
2) To do this week | 1) Set up Github repositry + Discord server + Java HTML application menus 2) GitHub navigation document 3) IntelliJ IDLE issues | Ethan
3) Road blocks | 1) Java Readiness + Research existing Companions apps + Troubleshooting IDLE 2) Further research Companion apps + animation state machines in Java e.g. Reaction system that selects actions that you can interrupt 3) Intellji IDLE issues | Nate
| 1) Went through Assignbment briefing and made a low fidelity demo for Desktop pet 2) Continue improving demo, implementing animation, AI 3) Debugging | Nick
| 1) Java Readiness (Late addition to the group Sixth member) 2) Catching up on Content and Java knowledge + Nate's research assistant 3) Being a late addition Sixth group member | Mak
Project set up | Are we allowed to use JavaSwing??? | Nate
| JavaFx can't do window click through | Nate
| Do we want it to go anywhere on the screen or a select field | Ethan
| Scale the transparent window | Nate
| Split Desktop pet functionality into must haves vs nice to haves -> User StoriesTab | Ethan
Pre-existing Codebases allowed
Nick ask about JavaSwing Gui. Email pending for Unit Coordinator. JavaSwing has functionality where you can click windows and it won't break
Each member responsible for Branch. Keep pushing to main to make sure code is Compatabile.
Start with a seed, Basic JavaFX project
GitHub documentation | Create new project > Java FX, Maven, name it Nothing needs to be ticked Terminal > git remote add origin [link] (github take https) > Hit Enter Git add . git commit - m "text" git pull Now you have the remote branches Click "Framework" and check the branches Check project folders Main>Java>project.esu>Launcher>Play button Ensure Computer has the external libraries for Java FX | Ethan
Troubleshooting | Git being Git. Defer | Ethan
| Pomodoro + add a database (this many hours of work) --> stretch goal Virtual currency. Build in tools that assist uses by suggesting work break, drink water and eat | Daniel
Core Functionality MUST HAVES | Getting it on the screen Base programming. Windows. JavaFX only, can't use JavaSwing unfortunately. | Nick
| How to Github step by step documentation | Ethan
| Ask Trivia questions (can simulate AI doesn't have to integrate AI. Ai integration can be a stretch goal. Implement AI first before we decide what its supposed to comment about AI). State machine | Ethan
| Animation Design - Nate's discretion. Rigging? Free assets can use see above meeting minutes points | Nate
| Programming for the Animation. Interact with pet by clicking. State machine. Built in tools | Jacob
| Boot up apps + One time menu screen + Catch up with Content | Mak

## 01.04.2026
Date | Wednesday, 1 April 2026
Start Time | 15:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate
Apologies | Nick, Makovin
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master Daniel | Daniel
| 1) Researched Pomodoro 2) User Stories + Implement basic Pomodoro functionality + Release Plan 3) Still learning Javascript | Daniel
1) Done last week | 1) Research design and rig-testing models 2) Implement the animation model (PNG method?) 3) No roadblocks currently | Nate
2) To do this week | 1) GitHub documentation and Mock Trivia branch code 2) SQL Storage for Trivia 3) Working Github [solved] | Ethan
3) Road blocks | 1) User stories 2) Research state changes for animation 3) Working Github [solved] | Jacob
| 1) Currently sick. Working on App Baseline Fucntionality. 2) Finish prototype Baseline Functionality and commit to Git. 3) Getting better :) | Nick

## 15.04.2026
Date | Wednesday, 15 April 2026
Start Time | 14:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Week 5-7 Retrospective
| User Stories + Implement basic Pomodoro functionality + Release Plan | Daniel
| Implement the animation model (PNG method?) | Nate
Review Project Tasks | SQL Storage for Trivia | Ethan
| Research state changes for animation and prototype | Jacob
| Finish prototype Baseline Functionality and commit to Git. | Nick
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Nate
| 1) research into timers, difficulted with fxml, user stories 2 ) get it working, start score system with a DB 3) struggles with figuring out java and fxml, merging issiues | Daniel
1) Done last week | 1) animating the character, creating sprite sheets, made basic style sheet. 2) help merging of branches, help with state machines.set up Trello 3) waiting on mass merg of classes before adding to the fire | Nate
2) To do this week | 1) made the trivia module and store data into a DB, ensureed it was ra, set up a test suit,2) merge to master branch 3) database issues but they are mainly fixed, git merges | Ethan
3) Road blocks | 1) mainly focused on the paper prototying, research into statemachains. 2) start working on the statemachine, 3) making it past the staticness of fxml | Jacob
| 1) finished the skeleton code for pulling up images, figuring out the logic 2) merg app, restructering to fit the rest of the program 3) waiting merger and debugging | Nick

## 22.04.2026
Date | Wednesday, 22 April 2026
Start Time | 14:30
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Daniel
| 1) Functional timer implementation timer + database research 2) Fixing buttons Timer + Database Pomodoro integration with Score 3) Needs further testing | Daniel
1) Done last week | 1) State changes code based off Nick's branch code and separating into code files 2) Combining state-machine with animation 3) None so far | Jacob
2) To do this week | 1) Merging all coding branches and debugging gitHub 2) Set up test suites for the others and implement Java documentation 3) Renamed SDK files | Ethan
3) Road blocks | 1) Set up Trello sprint plan for others to contribute , Finalising animation 2) Integrating the animation with the state machine code, setting up Animation Classes to get 3) Unsure if will work with current State Machine | Nate
| 1) Finished coding Skeleton code Double checked Pomodoro, Trivia and other code to see how they merge. 2) Start on merging everything with Skeleton code. 3) Understanding other team mates code. | Nick

## 29.04.2026
Date | Wednesday, 22 April 2026
Start Time | 14:00
End Time | 19:00
Attending | Daniel, Ethan, Jacob, Nate, Nick
Apologies
Item | Summary | From
Activity 1 Scrum Meetings | Scrum Master | Jacob
| 1) Refining pomodoro timer, making sure the timer doesnt duplicate, sophisticating the database 2) adding documentation and proper testing 3) test suite | Daniel
1) Done last week | 1) Refining the state change machine, implementing UI and animations 2) Ironing out bugs, polishing the UI, Javadoc comments 3) javadocs comments | Jacob
2) To do this week | 1) Set up javadoc automation, a lot of merging of branches (A LOT), javadocs commenting for trivia section, overlay for trivia with desktop pet 2) polishing UI for the trivia when called, helping merge and everything stable 3) INTELLIJ SUCKS | Ethan
3) Road blocks | 1) Worked on setting up on image sequences, and made it customisable and simpler to call 2) Adding in Javadocs comments and fixing up animations and colour variants 3) No roadblocks thanks Ethan | Nate
| 1) Merging branches together to get it working together for transparent prototype, adding features (timer, pomodoro) 2) UI and feature box 3) debugging | Nick

## User stories
Functionality Ideas |  | Must Haves | Should have | could have | Won't have
Idle actions
Interact with pet by clicking |  | Y
locked at bottom 1/4 of screen
asks random trivia questions (simulating AI) |  | y
Pomodoro Timer, Logging successful sessions on database |  | Y
shake the pet it gets mad
click pet it gets happy
ignore/neglect pet it gets sad
Konami Code
Sound effects
Virtual currency for successful Pomodoro sessions
Build in tools that assist uses by suggesting work break, drink water and eat |  | Y
required animations | idle | BLOCKED
| walking (types?) | BLOCKED LEFT AND RIGHT
interaction
reacting
sleeping
state transition
timed events
random events
talking
| jumping | BLOCKED
yawning
| blinking | IN THE IDLE
sneezing
head tilt
hanging while picket up
| crying | TOO MUCH WORK
| interact with props | no props added /made
wave
speaking
| give coin to user | very much a stretch goal
wide eye stare into camera
required expressions | happy | done
| sad | done
bored
confused

## Sprint Plan OLD
| User Stories Summary | Week 5 | Week 6 | Week 7
Daniel | Pomodoro | Researching functionality | Implemented basic functionality | Uploaded Pomodoro GUI
Ethan | Trivia | Mock Trivia branch code | SQL Storage for Trivia | Set up the TriviaModule test suit
Jacob | State Machine | Low fidelity paper prototype | Research state changes | Implementing state change machine
Nate | pet creation/ finding | animations | creating sprite sheets | sql database to store anims
Nick | Skeleton | Low fidelity pet demo | Baseline functionality | Merging together